## Introduction
[Insert Department/Project Logo] |  |  | [Insert Department Name] [Insert Project Name]
Introduction to the Requirements Traceability Matrix Template
The Requirements Traceability Matrix (RTM) is a reusable tool for collecting and establishing requirement links to their origin so they may be traced throughout the project lifecycle. The RTM links each requirement to business needs and goals as well as project objectives helping to ensure business value.
The following sections provide instruction and guidance for the use of the Requirements Traceability Matrix (RTM) tool to guide the reader into understanding the RTM tool purpose and how to complete it.
Template style conventions are as follows:
Style |  | Convention
Normal text |  | Indicates placeholder text that can be used for any project
[Instructional text in brackets] |  | [Indicates text that is to be replaced/edited/deleted by document author]
Example text in italics |  | Indicates example text that might be replaced/edited/deleted by user
Project Sample Library: The CA-PMF has a Project Sample Library that contains real-world project artifacts from approved projects that you can reference to help you complete CA-PMF templates. Visit the CA-PMF website to access the Project Sample Library.
CA-PMF website: | http://capmf.cio.ca.gov/

## Instructions
[Insert Department/Project Logo] | [9 empty] | [Insert Department Name] [Insert Project Name]
Requirements Traceability Matrix Template
1 Introduction
[Requirements traceability is a structured way to keep track of requirements. Requirements are linked or mapped back to their source and followed as more detailed requirements are defined throughout the project. This activity may also involve capturing relationships between many development lifecycle objects.]
[Tracing requirements back to their source is sometimes called backward or upwards traceability. It involves linking requirements to the identified business problems or needs, business goals, and project objectives.]
[Tracing requirements throughout the project is called forwards allocation or forwards traceability. It involves documenting the linkage between requirements, and the linkage between requirements and the design, development, testing, and deployment work products.]
[Tracing requirements through the entire lifecycle helps confirm that technical requirements have been satisfied by functional requirements, which will in turn satisfy business requirements. This spans from project scope to high-level requirements to detailed design, down through coding and testing.]
2 Roles and Responsibilities
[Describe who, and in what role, is going to be responsible for performing the various activities described in the Plan and the relationship of all involved.]
Name | Roles | Responsibility
| Project Sponsor | • Approve the Requirements • Review and approve Functional Requirements • Provide overall business leadership to ensure the requirements baseline is maintained • Ensure requests for requirement changes have followed the approved Change Management Process, and that approved changes to the baseline have been timely incorporated into the requirements baseline
| IT Sponsor | • Approve the Requirements • Review and approves Functional Requirements (or System Requirements for hardware/network projects) • Provide overall guidance and mentoring
| Project Manager | • Lead a team in the development of the Requirements • Provide regular status and make approval recommendations for requirements • Ensure the overall Requirements Management effort is being executed in accordance with the Plan • Ensure the entire project team, state and vendor (if applicable) are following the Plan and ensure all other project processes that interact or provide input to the Requirements Management effort are being adhered to • Ensure there are sufficient resources to execute the Plan and that requirements traceability activities are being performed in a timely manner
| Test and Quality Managers (if applicable) | • Review and participate in requirements gathering and traceability activities • Ensure the overall requirements traceability activities are coordinated with testing and quality activities and plans
| Requirements Lead | • Along with the Project Manager and Requirements Analyst, develop the Requirements Traceability Matrix • If available, report to the Project Manager; has overall responsibility managing processes and activities outlined for requirements traceability • Responsible for the overall requirements traceability effort and requirements repository updates
| Requirements Analyst(s) | • Assist in the development of the Requirements Traceability Matrix
| Business Owner(s) | • Review and recommend approval the Requirements Traceability Matrix • Participate in the Requirements Analysis status review • Review requirements management reports to ensure the requirements baseline is complete, that all approved changes have been incorporated, and impacts caused by changes are identified within the repository
| Business Subject Matter Expert(s) | • Participate in process to develop the Requirements Traceability Matrix • Attend the Requirements Analysis and Development status reviews
| Department of Technology | • Review Requirements Traceability Matrix
| Vendor Project Manager | • If applicable, ensure the vendor team is complying with the requirements management process and procedures within this Plan and in accordance with requirements in the vendor’s contract • Perform reviews of the requirements traceability work performed by the vendor team and verify that work complies with the requirements management process and requirements in the vendor’s contract • Identify issues to the Project Manager in a timely manner to minimize the amount of rework necessary for state and vendor teams
3 RTM Attributes
[The Requirements Management Tool (RTM) tool provided in the next section consists of the following attributes. Attribute descriptions are provided to help understand usage.]
• ID - A unique ID number used to identify each requirement.
• Assoc. ID - This column should contain IDs of any associated utilities used for requirements tracking such as repository, pipeline document, etc.
• Category - This column is populated with the requirement category of to the functional area the requirement is related to during product development.
• Requirement Description (Business Needs, Goals, Objectives, Technical Assumption(s) and/or Customer Need(s) - This column is populated with a requirement description linked to the specific requirement classification (functional, non-functional, etc.).
o Requirement Type & Description (Functional, Non-functional, etc.) - This column is populated with the requirement type and a clearly understood requirement description.
o Links to Other Requirement IDs - List the ID numbers of other requirements that are linked by functionality.
o Classification (Mandatory or Optional) - Indicate if the requirements is mandatory or optional.
o Status (Met Y/N?) - This column is populated with current status of the requirement development to determine if the requirement has been met or not.
o Design Document Reference - This column is populated with a description of the architectural/design document linked to the requirement.
o Technical Specification Reference - This column is populated with a description of the technical specification linked to the requirement.
o WBS Deliverables Reference - This column is populated with a description of the WBS deliverables linked to the requirement (e.g. this could include references to the software components and software modules for that type of project).
o Test Case Number - This column is populated with the test case number linked to the functional requirement.
o Tested In - This column is populated with the module/test environment the functional requirement has been tested in.
o Implemented In - This column is populated with the module/environment the functional requirement has been implemented in.
o Verification Date - This column is populated with the verification date of when the requirement was met.
4 RTM Example
ID | Assoc. ID | Category | Requirement Description (Business Needs, Goals, Objectives, Technical Assumptions and/or Customer Needs) | Requirement Type & Description (Functional, Non-Functional, etc.) | Links to other Req. IDs | Classification (Mandatory / Optional) | Design Doc Reference | Technical Spec Reference | WBS Deliverables Reference | Test Cases Reference | Tested In | Implemented In | Status (Met Y/N?) | Verification Date
1 | 1.0.0 | Business Rules | The system shall support Users by providing an environment for creation, modification and general management of business rules. | Functional | 1.1.0, 11.2.0, 11.2.3, 15.2.0 | Mandatory | System design doc v2 dated 06/01/16. | System Req. Spec. (SRS) v3 dated 08/01/16. | WBS #4.1.1 and 4.1.2.
| 1.1.0 | Business Rules | The system shall support Users by providing a user interface (UI) which supports visualization of the full set of configured business rules. | Functional | 1.0.0, 11.2.0, 11.2.3, 15.2.0 | Mandatory | System design doc v2 dated 06/01/16. | System Req. Spec. (SRS) v3 dated 08/01/16. | WBS #4.1.1 and 4.1.2.
1.2.0
1.2.1
2 | 2.0.0 | Reporting | The Reporting Component shall support Users in the creation, maintenance, and execution of Reports via a Reporting Management user interface (UI). | Functional | 2.1.0, 15.1.0, 15.2.1, 15.2.3 | Mandatory | System design doc v2 dated 06/01/16. | System Req. Spec. (SRS) v3 dated 08/01/16. | WBS #8.3.1 and 8.3.2.
2.1.0
2.2.0
2.2.1
3 | 3.0.0
3.1.0
3.2.0
3.2.1
4 | 4.0.0
4.1.0
4.2.0
4.2.1

## Requirements Traceability
[Insert Department/Project Logo] | [11 empty] | [Insert Department Name] [Insert Project Name]
Requirements Traceability Matrix
ID | Assoc. ID | Category | Requirement Description (Business Needs, Goals, Objectives, Technical Assumptions and/or Customer Needs) | Requirement Type & Description (Functional, Non-Functional, etc.) | Links to other Req. IDs | Classification (Mandatory / Optional) | Design Doc Reference | Technical Spec Reference | WBS Deliverables Reference | Test Cases Reference | Tested In | Implemented In | Status (Met Y/N?) | Verification Date